## Instructions
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
Instructions
1 | List the team members name above the block
2 | Title is a place to give a 1-3 word descritpion of the task for quick reference
3 | Description is a more detailed descrition of the task and should include acceptance critieria for the reviewer
4 | Initial Est is the expected number of hours needed to complete the task
5 | Change is to adjust your estimate. Use negative numbers if it took less time. Use Postitve values if it took more time.
6 | Completed is how many hours you have spent on the task.
7 | Testing is the date when you started testing your own code
8 | To Review is the date you deemed it complete and submitted it for review
9 | Submitted is the date when you finished making the adjustments suggested by the review and uploaded it to the collective group code.
10 | Reviewer is the person who completes the task review. Note this should happen even if there is no code.
11 | Code is where the file that your data can be found. This might be a text document if you were doing a non-coding tasking.
12 | TestCases is where the file that your test case can be found. This box may be blank if there was no implementation for this task.

## Burn Down Charts
SPRINT 0 | Total Hours
Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Hours Left | 72 | 72 | 72 | 69 | 61 | 61 | 61 | 41 | 41 | 36 | 32 | 17 | 12 | 12 | 6
Member 1 | 12
Member 2 | 12 | 2: 3
Member 3 | 12 | 3: 8; 6: 20; 8: 5
Member 4 | 12 | 9: 4; 10: 15; 13: 6
Member 5 | 12 | 11: 5
Member 6 | 12
SPRINT 1 | Total Hours
Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Hours Left | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
Member 1 | 12
Member 2 | 12
Member 3 | 12
Member 4 | 12
Member 5 | 12
Member 6 | 12
SPRINT 2 | Total Hours
Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Hours Left | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108
Member 1 | 18
Member 2 | 18
Member 3 | 18
Member 4 | 18
Member 5 | 18
Member 6 | 18
SPRINT 3 | Total Hours
Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Hours Left | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
Member 1 | 12
Member 2 | 12
Member 3 | 12
Member 4 | 12
Member 5 | 12
Member 6 | 12
SPRINT 4 | Total Hours
Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Hours Left | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72
Member 1 | 12
Member 2 | 12
Member 3 | 12
Member 4 | 12
Member 5 | 12
Member 6 | 12

## Sprint 0
TEAM MEMBER: |  | Caleb Fields
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Client Meeting | Initial meeting with client | 2 | -1 | 1 |  |  |  | Abdallah
2 | Team Meeting | Discussion of project status and class assignments | 2 | 0 | 2 |  |  |  | Abdallah
3 | Plan Sprint 1 | Create Sprint Plan | 1 | 0 | 1 |  |  |  | Abdallah
4 | Class Assignments | Work with team to complete assignments for class | 3 | -1 | 2 |  |  |  | Abdallah
5 | Discussion Board | Read prompt, respond, read replies, discuss | 1 | 0 | 1 |  |  |  | Abdallah
6 | Programming Practice | (Re)familiarize myself with the programming language selected for the project | 3 | 0 | 3 |  |  |  | Abdallah
7 | Database Setup | Decide which database to use + set it up | 1 | 0 | 1
8
9
10
TEAM MEMBER: |  | Ben Handshoe
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Client Meeting | Initial meeting with client | 2 | -1 | 1 |  |  |  | Calvin
2 | Team Meeting | Discussion of project status and class assignments | 2 | 0 | 2 |  |  |  | Calvin
3 | Plan Sprint 1 | Create Sprint Plan | 1 | 0 | 1 |  |  |  | Calvin
4 | Class Assignments | Work with team to complete assignments for class | 3 | -1 | 2 |  |  |  | Calvin
5 | Discussion Board | Read prompt, respond, read replies, discuss | 1 | 0 | 1 |  |  |  | Calvin
6 | Programming Practice | (Re)familiarize myself with the programming language selected for the project | 3 | 0 | 3 |  |  |  | Calvin
7 | Node Setup | Create Node class for displaying data | 3
8 | Create design document
9
10
TEAM MEMBER: |  | Calvin Higdon
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Client Meeting | Initial meeting with client | 2 | -1 | 1 |  |  |  | Ben
2 | Team Meeting | Discussion of project status and class assignments | 2 | 0 | 2 |  |  |  | Ben
3 | Plan Sprint 1 | Create Sprint Plan | 1 | 0 | 1 |  |  |  | Ben
4 | Class Assignments | Work with team to complete assignments for class | 3 | -1 | 2 |  |  |  | Ben
5 | Discussion Board | Read prompt, respond, read replies, discuss | 1 | 0 | 1 |  |  |  | Ben
6 | Programming Practice | (Re)familiarize myself with the programming language selected for the project | 3 | 0 | 3 |  |  |  | Ben
7 | Import JSON File | Create interface in application window to load JSON file and display it | 1 | 0 | 1 | 2025-01-28 | 2025-01-28 | 2025-01-28 | Abdallah | main.py
8 | Toolchain Documentation | Create documentation for toolchain setup | 1.5
9 | Create python exec | Create an executable using python to test file size | 1
10
TEAM MEMBER: |  | Abdallah Sher
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Client Meeting | Initial meeting with client | 2 | -1 | 1 |  |  |  | Caleb
2 | Team Meeting | Discussion of project status and class assignments | 2 | 0 | 2 |  |  |  | Caleb
3 | Plan Sprint 1 | Create Sprint Plan | 1 | 0 | 1 |  |  |  | Caleb
4 | Class Assignments | Work with team to complete assignments for class | 3 | -1 | 2 |  |  |  | Caleb
5 | Discussion Board | Read prompt, respond, read replies, discuss | 1 | 0 | 1 |  |  |  | Caleb
6 | Programming Practice | (Re)familiarize myself with the programming language selected for the project | 3 | -1 | 2 |  |  |  | Caleb
7 | Create codebase | Create initial codebase with entrance script to launch a new window | 1 | 0 | 1 | 2025-01-27 | 2025-01-27 | 2025-01-28 | Calvin | main.py
8 | Create design document
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10

## Sprint 1
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10

## Sprint 2
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10

## Sprint 3
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10

## Sprint 4
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10